## Slide 1: Computer Contracts
Part-2

## Slide 2: Payment terms
Payment shall become due within thirty days of the date of issue of an invoice.
If payment is delayed by more than thirty days from the due date, the Company shall have the right, at its discretion, to terminate the contract, or to apply a surcharge at an interest rate of 2 per cent above the bank base lending rate.
In practice, such clauses are only brought into effect in extreme cases, since using them is likely to destroy the goodwill between supplier and client on which the success of the project depends.
Notes: Discretion: the freedom to decide what should be done in a particular situation.
the minimum rate set by the Reserve Bank below which banks are not allowed to lend to its customers
Banks used to follow the Base Lending Rate (BLR) to determine the interest rate to apply to your home loan

## Slide 3: Payment terms
Specify pattern of payments
an initial payment of, say, 15 per cent of the contract value becomes due on signature of the contract;
further stage payments become due at various points during the development, bringing the total up to, say, 65 per cent;
a further 25 per cent becomes due on acceptance of the software
the final 10 per cent becomes due at the end of the warranty period.
Notes: Premium:an amount to be paid for a contract of insurance

## Slide 4: Calculating payments for delays and changes
when the client fails to provide information on a due date or when changes are requested which result in extra work.
The contract must specify the process by which these extra payments are to be calculated
annex will include daily charging rates for each grade of staff employed on the contract and the amount of extra effort to be paid for will be agreed at progress meetings.
Delay payments and payments for variations to the original requirements are, perhaps, the commonest cause of contractual disputes, not only in software engineering but in most other contracting industries

## Slide 5: Penalty clauses
The normal mechanism used is to include a penalty clause which provides that the sum payable to the supplier is reduced by a specified amount for each week that acceptance of the product is delayed, up to a certain maximum
Suppliers are very reluctant to accept penalty clauses
If the contract is to include penalty clauses, the bid price is likely to be increased by at least half the maximum value of the penalty.
If the software is seriously late and penalties approach their maximum, there is little incentive for the supplier to complete the work since he will already have received in stage payments as much as he is going to get
It should be realized that the cost of delays on fixed price contracts is very high, regardless of penalty payments. Every delay eats into the supplier’s profit margin. As a result, suppliers are strongly motivated to produce the software on time and delay is usually the result of genuine technical difficulties (or incompetence!) rather than lack of motivation.

## Slide 6: Obligations of the client
client will have to fulfil certain obligations if the contract is to be completed successfully.
provide documentation on aspects of the client’s activities or the environment in which the system will run;
provide access to appropriate members of staff;
provide machine facilities for development and testing;
provide accommodation, telephone and secretarial facilities for the company’s staff when working on the client’s premises;
provide data communications facilities to the site.
failure to meet the obligations may render the client liable for delay payments

## Slide 7: Standards and methods of working
supplier is likely to have company standards, methods of working, quality assurance procedures, etc. and will normally prefer to use these
More sophisticated clients will have their own procedures
In some cases, the supplier may be required to allow the client to apply quality control procedures to the project.
The contract must specify which is to apply.

## Slide 8: Progress meetings, Project Managers, Acceptance procedure
Progress meetings: Regular progress meetings are essential to the successful completion of a fixed price contract and it is advisable that standard terms and conditions require them to be held.
Project Managers: The Project Managers must have at least the authority necessary to fulfil the obligations which the contract places on them.
Acceptance procedure: critical part of any fixed price contract, successful completion of the contract is judged, client should provide a fixed set of acceptance tests and expected results and that successful performance of these tests shall constitute acceptance of the system

## Slide 9: Warranty and maintenance
Once the product has been accepted, it is common practice to offer a warranty period of, typically, 90 days.
Any errors found in the software and reported within this period will be corrected free of charge.
This clause is, of course, subject to negotiation; reducing or eliminating the warranty period will reduce the overall cost of the contract prolonging the period will increase it.
Once the warranty period is over, the supplier may offer, or the client demand, that maintenance will continue to be available on request.

## Slide 10: Termination of the contract
Termination of the contract:
the client to be taken over by another company which already has a system of the type being developed, or for a change in policy on the part of the client to mean that the system is no longer relevant to its needs.
supplier is to be paid for all the work carried out up to the point
together with some compensation for the time needed to redeploy staff on other revenue-earning work.
The question of ownership of the work so far carried out must also be addressed.

## Slide 11: Arbitration
Court action to resolve a contractual dispute is likely to be expensive.
It is common practice for contracts to include a statement that, in the event of a dispute that cannot be resolved by the parties themselves, they agree to accept the decision of an independent arbitrator.
British Computer Society or by the President of the Institution of Electrical Engineers both bodies maintain lists of qualified arbitrators who have the necessary technical understanding.
Some organizations may be unwilling to accept an arbitration clause because they feel that they are signing away some of their legal rights.
Notes: Arbitration is a procedure in which a dispute is submitted, by agreement of the parties, to one or more arbitrators who make a binding decision on the dispute

## Slide 12: Inflation
commitment to long term maintenance, the supplier will wish to ensure protection against the effects of unpredictable inflation
include a clause which allows charges to be increased in accordance with the rise in costs
The clause should state how often (once a year, twice a year) charges can be increased and how the effect on the overall price is to be calculated
Applicable law: Where the supplier and the client have their registered offices in different legal jurisdictions or performance of the contract involves more than one jurisdiction, it is necessary to state under which laws the contract is to be interpreted

## Slide 13: Other types of software services contract
There are four types of contractual arrangement which are widely used in connection with the provision of software services:
contract hire;
time and materials;
consultancy;

## Slide 14: contract hire
the supplier agrees to provide the services of one or more staff to work for the client;
staff work under the direction of the client and the supplier’s responsibility is limited to providing suitably competent people and replacing them if they become unavailable or are adjudged unsuitable by the client
Payment is on the basis of a fixed rate for each man day worked; the rate depends on the experience and qualifications of the staff
Issues such as delay payments, acceptance tests and many others simply do not arise

## Slide 15: Time and materials
A time and materials contract (often referred to as a “cost plus” contract) is somewhere between a contract hire agreement and a fixed price contract.
The supplier agrees to undertake the development of the software in much the same way as in a fixed price contract but payment is made on the basis of the costs incurred, with labor charged in the same way as for contract hire
This is a type of contract that pays the contractor for the materials he or she uses as well as the amount of time spent to finish the job.
A time and materials contract usually signals to the customer that there is risk involved. The project could cost more than initially anticipated.
The supplier is not committed to completing the work for a fixed price, although a maximum payment may be fixed beyond which the project may be reviewed
Notes: For example, Joe the contractor has just been contacted by a homeowner who wants him to design and build a saltwater fish tank in the middle of the homeowner's home. Since this is a custom job and requires Joe to work on part of the house, Joe uses a time and materials contract to make sure he gets paid what he needs in order to do the job. This type of contract has the homeowner paying Joe for any materials he needs as well as all the time he needs to put in to finish the custom built tank.

## Slide 16: Time and materials
Many of the complications of fixed price contracts still occur with time and materials contracts—ownership of rights, facilities to be provided by the client, progress monitoring arrangements, for instance—but others,
such as delay payments and acceptance testing do not;
this is not to say that no acceptance testing is done, only that it has no contractual significance since nothing contractual depends on its outcome
Time materials or fixed price, which one would you prefer ?
Notes: For example, Joe the contractor has just been contacted by a homeowner who wants him to design and build a saltwater fish tank in the middle of the homeowner's home. Since this is a custom job and requires Joe to work on part of the house, Joe uses a time and materials contract to make sure he gets paid what he needs in order to do the job. This type of contract has the homeowner paying Joe for any materials he needs as well as all the time he needs to put in to finish the custom built tank.

## Slide 17: Consultancy contract
You hire team of consultants
Consultants are typically used to assess some aspect of an organization and to make proposals for improvements.
The end product of a consultancy project is therefore usually a report or other document
Consultancy projects are usually undertaken for a fixed price but the form of contract is very much simpler than the fixed price contracts so far described